## Sheet1
| Completed | September 2023 |  |  |  | October 2023
ACTIVITY | Prev Weeks | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
1. Literature Review
1.1 Read ISAR theory & understand concepts | a
1.2 Develop headings | a
1.3 Identify papers that justify the problem statement | a
1.4 Identify available algorithms and narrow-down for this application | bar: September 2023 Week 2
1.5 Complete bullet points for each section | bar: September 2023 Week 3
2. Design
2.1 Identify user requirements and system specifications | a
2.2 Determine submodules | a
2.3 Identify algorithms to use and choose which to implement | a
2.4 Identify metrics for performance comparison | a
3. Implementation
3.1 Produce pseudo code for (2) range-alignment (RA) algorithms | a
3.2 Initial implementation of (2) RA algorithms | a
3.3 Produce pseudo code for (2) autofocus (AF) algorithms | bar: September 2023 Week 1
3.4 Initial implementation of (2) AF algorithms | bar: September 2023 Week 1
3.5 Final Implementation: clean up code & utilise MATLAB functionality to increase efficiency | bar: September 2023 Week 1
3.6 Build Quick-look proceessor using best combination of RA and AF | bar: September 2023 Week 4
4. Tentative - Verification Testing
4.1 Create ISAR data simulator
4.2 Use simulated data to test algorithms
5. Process measured data
5.1 Dataset 1: run through all algorithms (2xRA and 2xAF) & record performance metrics | bar: September 2023 Week 2
5.2 Dataset 2: run through all algorithms (2xRA and 2xAF) & record performance metrics | bar: September 2023 Week 2
5.3 Dataset 3: run through all algorithms (2xRA and 2xAF) & record performance metrics | bar: September 2023 Week 2
5.4 Compare performance and identify best combination of RA and AF | bar: September 2023 Week 2
6. Write-up report
6.1 Develop skeleton of report - chapter names + section headings | bar: September 2023 Week 1
6.2 Write up draft Chapter 1 introduction in bullet points + submit for review | bar: September 2023 Week 2
6.3 Write up draft Chapter 2 in bullet points + submit for review | bar: September 2023 Week 4
6.4 Write up draft Chapter 3 in bullet points + submit for review | bar: September 2023 Week 3
6.5 Write up draft Chapter 4 in bullet points + submit for review | bar: September 2023 Week 2
6.6 Write up draft Chapter 5 in bullet points + submit for review | bar: September 2023 Week 3
6.7 Write up draft Chapter 6 in bullet points + submit for review | bar: September 2023 Week 3
6.8 Write up draft Chapter 7 in bullet points + submit for review | bar: September 2023 Week 4
6.9 Write up draft Chapter 8 in bullet points + submit for review | bar: October 2023 Week 1
6.10 Write up Chapter 1 introduction in full sentences + paragraphs | bar: October 2023 Week 1
6.11 Write up draft Chapter 2 in full sentences + paragraphs | bar: October 2023 Week 2
6.12 Write up draft Chapter 3 in full sentences + paragraphs | bar: October 2023 Week 1
6.13 Write up draft Chapter 4 in full sentences + paragraphs | bar: October 2023 Week 2
6.14 Write up draft Chapter 5 in full sentences + paragraphs | bar: October 2023 Week 2
6.15 Write up draft Chapter 6 in full sentences + paragraphs | bar: October 2023 Week 3
6.16 Write up draft Chapter 7 in full sentences + paragraphs | bar: October 2023 Week 3
6.17 Write up draft Chapter 8 in full sentences + paragraphs | bar: October 2023 Week 3
6.14 Pass chapters through grammarly.com and correct mistakes | bar: October 2023 Week 4
6.15 Finalise list of references | bar: October 2023 Week 4